Tentative title

A survey on ---

Group members

Louise Johnson B00815919

Matthew Smith

Selected research paper

* select research paper
  + include the list of authors, paper title, publication venue, publication time

Project timeline

March 8:

* Decide on research paper
* Submit project proposal

March 13:

* Prepare an outline of the project report
* Divide up sections of report among group members (intro, problem description, algorithm description, data preparation and algorithm implementation, experimental results and conclusion)
* Discuss implementation of project code, and map out intended implementation

March 20:

* Prepare rough draft of assigned project report sections
* Begin implementing project code

March 27:

* Finalize slides and divide up presentation parts
* Derive experimental results from project code

March 31:

* Rehearse presentation with final slides

April 5:

* **Submit** slides
* Give presentation (on April 5th)

April 10:

* Finalize the project report.

April 17:

* Assign final edits of project code and project report

April 19:

* Submit project code and project report